## Sheet1 (hidden)
Skill | Responsibilities
Azure AD | Excellent handson experience with Azure Active Directory implementation
Azure SSO implentation | Knowledge on SSO/MFA/RBAC implementation
Spring Boot | Handson experience with spring security configurations across different end points
Spring Security | Create new features & functionalities whilst implementing backend data services into the product
Mojina
Frontend | Take ownership and responsibility for the front end development
Javascript /Type Script | Good knowledge on CSR/SSR implementation
Node JS/NPM package manager | Good knowledge on CSR/SSR implementation
Database | Understanding of databases and querying techniques
CSS/HTML | Knowledge on any meterial/bootsrap design
CICD pipeline | Good knowledge on CICD pipeline
GIT - Branching/Merging
Jenkins

## Sheet2 (hidden)
S.N | Task | Comments
1 | Mujina setup in local environment for IDP and SP (Depolyments)
2 | Mujina configuration on Service Provider - Front end Angular
3 | Mujina configuration on Service Provider - Back end Spring boot
4 | SSO setup for Angular - using IDP/SP mujina
5 | SSO setup for Spring boot - using IDP/SP mujina
6 | SSO Test user id creation lower environments using Mujina IDP
7 | Strategy to manage configurations Azure AD (production) Vs Mujina (non - production) - Single code base
8 | Signature /policy generation using mujina for SAML , It need to be investigated further
9 | SSO implemetation on azure AD - for Angular (Front end) - production
10 | SSO implemetation on azure AD - for Spring boot (Back end) - production
11 | CICD pipeline setup for Mujina - need to clarified on the Devops
12 | Current application knowledge that needs SSO implentation (Angular/Spring boot)
13 | Quantify the number of end-points needed for SSO implentation on the API specifications.
14 | LLD not yet prepared - Need to see specifications
15 | Angular Session management as part of new IDP solution
16 | Logout functiaonlity / Cookie management on SSO with Angular
17 | Key vault configurations on the certificate/password/any credentials
18 | Technical training on Mujina / Azure AD
S.No | challengaes - QA | Reference
1 | Mujina no support community available | https://stackoverflow.com/questions/40581068/how-to-add-an-external-sp-service-provider-in-mujina-idp-identity-provider
2 | Lack of documentation on SP (Service Provider) configuration using SAML 2.0
3 | Lack of documentation on IDP (Identity provider) configuration using SAML 2.0
4 | No Prototype available on the Mujina front end /backend implementation
5 | As we are implementing SSO in lower invironment using Mujina and in production planning using Azure AD, need atleast 1 production like (Azure AD) environment for testing.
S.No | Recommendations
1 | is it possible to convinience the client to use Azure AD in all the lower environments as well. This is due to dependency on the old technololgy and no official support available at this moment

## SSO Challenges
SSO Implementation challenges/open issues & Efforts
S.N | Efforts Tracking | Actual Effort (Business Days)
1 | Onboarding process - TELFORD/BPSS | 2
2 | Knowledge transfer - As is process | 1
3 | Knowledge transfer - SSO development on API Gateway | 1
4 | Software installation and configuration setup | 1
5 | Access management with HMRC - Jira, Confluence, repo ,etc | 1
6 | Local setup for Mujina IDP | 1
7 | Local setup with Mujina configuration on API Gateway | 1
8 | Local setup with Cris angular application | 1
9 | Managing and resolving Cross origin issues with API Gateway/Chris applications | 3
10 | Managing and resolving SSL certificate issues with API Gateway/Chris applications | 3
11 | Managing and resolving SSO redirection issues for initial authentication with Mujina IDP | 3
12 | Managing and resolving conflicts around SAML response token handling mechanism with API Gateway | 3
13 | Resolving issues around session management, cookies, Local storage on API gateway/Chris applications | 1
14 | Proof of concept on initial authentication/redirection with API gateway/Chris applications | 5
15 | Proof of concept on SSO API call implementation with API gateway/Chris applications | 5
Total Efforts (Business Days) |  | 32
S.N | Challenges Experienced | Complexity/Status
1 | API gateway microservices were not accessible due to SSL certificates issues | Medium/Resolved
2 | API communication with Chris angular front end application with API Gateway were not functioning due to CORS issues | Medium/Resolved
3 | Authentication with API gateway and Mujina IDP were not functioning due to CORS issues | Easy/Resolved
4 | Mujina IDP login page for authentication was not functioning due to redirection issues | Complex/Resolved
5 | Mujina IDP SAML response was not able to capture due to exceeding maximum length of auth token | Complex/Un-Resolved
6 | Mujina IDP session management cookies were not able to capture at Chris application due to cross origin domain | Medium/Resolved
7 | CRIS UI setup to stop basic authorisation with existing functionality | Easy/Resolved
8 | API gateway not able to connect on local end points are not responding from POSTMAN | Medium/un-Resolved
9 | The CRIS Front end application not able to accept the POST calls from IDP (Mujina) | Medium/Resolved
10 | Installation and issues around mujina open source repository (SP/IDP) | Complex/Resolved
11 | Redirection after authentication by mujina not functioning due to code base issue with API Gateway (POC) | Complex/Resolved
12 | Issues around after redirection for MS endpoint calling to get the search result (POC) | Complex/Resolved
13 | Issues around deploying the code base with DEV/Test environments | Partially resolved
S.No | Open challenges | Comments
1 | Redirection after SSO authentication is not working actual code base (API Gateway)
2 | CRIS angular application was in very old version - Migration may require to manage SSO
3 | CRIS angular application using client side rendering can't be SP (means can't manage SAML response tokens/Metadata/certificates)
4 | Angular NPM packages may require upgrade in CRIS application
5 | API Gateway using very old version of Spring boot - Migration may require to manage SSO
6 | API Gateway using older version of Java (version 6) on SAML authentication - Migration may require
7 | API Gateway end points were not accessible due to code base issue, always redirects with default port (8443)
8 | API gateway and corresponding micro service communication were complex to understand
9 | No community/Forum/Support teams available for Mujina identify management
10 | Very limited technical documentation available for API Gateway/Mujina/Cris application
11 | No implementation/prototype/POC availabe for Mujina implementation .(including HMRC/cognizant/outside cognizant)
12 | Number of issues reported about mujina IDP by outside world, most of them un-resolved by OpenContext (Owner for Mujina)
13 | No technical training available for Mujina
14 | Future enhancements/Modification with Mujina IDP becomes cumbersome process for HMRC (since its 3rd party - no support available)